
GUYANA NATIONAL BUREAU OF STANDARDS
STANDARDS DEVELOPMENT WORK PROGRAMME 
 JANUARY 2026 TO JUNE 2026
[image: image1.png]\ /

ok,

GNBS

()

ISO 9001:2015 CERTIFIED
ISO/IEC 17025:2017 ACCREDITED




“Creating a culture of quality through standards”

Strategic Theme 2:
Enabling the National Quality Infrastructure (NQI).
Strategic Goal 2: 
Promoting and Supporting the Implementation of the NQI.
Objective 1:
Increase the development, use and revision of standards relevant to Guyana’s   Emerging Sectors by 10% by 2027.
Objective 2:
To incorporate the use of standards in the Public Procurement System by 15 Ministries by 2027.
Objective 3:
To increase the use of Codex standards by local businesses.
Guyana National Bureau of Standards (GNBS) 

Track MB, Block B

National Exhibition Centre, Sophia 

Telephone: 592-219-0064-66 
Email: standards@gnbsgy.org
Website: www.gnbsgy.org
© GNBS 2026
	NO.
	OBJECTIVES
	ACTIVITIES
	
	PERFORMANCE INDICATORS
	OUTPUTS
	
	OUTCOMES 
	TIME FRAME

	2.1
	To submit at least thirty-three (33) standards to the National Standards Council (NSC) for approval by December 31, 2026.
	2.1.1 Conduct Technical Committee meetings to review (draft) standards.

2.1.2 Conduct public consultations sessions with stakeholders and receive comments on draft standards.

2.1.3 Submit final draft standards to the National Standards Council (NSC) for approval.

2.1.4 Conduct standards review surveys of national standards.

2.1.5 Revise national standards

2.1.6 Adopt regional/international standards to be used nationally. 

2.1.7 Adopt with modification regional/international standards to be used nationally.

2.1.8 Update the Standardisation Department Work Plan
	
	Completed/updated Work Programme

Number of Public Consultations conducted.

Number of standards approved.

Number of standards developed.

Number of standards reviewed.

Number of standards revised.

Number of standards adopted.

Number of standards adopted with modification.

	Public Consultations

Sessions

Approved National Standards 
	
	Approved national standards

	January 2026-December 2026

	2.2
	To review at least eight (8) compulsory standards by December 31, 2026.
	2..2.1 Conduct standards review surveys of national standards.
2.2.2 Conduct meetings to review the standard if needed.

2.2.3 Collate the review results and prepare the Standards Review Results form.


	
	Number of compulsory standards reviewed.

	Compulsory standards to be confirmed.

Compulsory standards recommended to be revised.

Compulsory standards to be amended.


	
	Updated compulsory standards

Reduction of non-compliant products and services on the market


	January 2026-December 2026

	2.3
	To actively participate in at least seven (7) CROSQ TMC and CROSQ Editorial Committee   meetings by December 31, 2026.
	2.3.1 Attend CROSQ TMC Online and Special Extraordinary Online meetings held.

2.3.2 Attend CROSQ TMC Face-to Face Meeting.
	
	Number of CROSQ TMC Meetings attended.
	Participation in CROSQ TMC Meetings
	
	Continued awareness of work being undertaken in regional standards development.

Continued access to the regional forum to share national inputs on regional standards development. 
	January 2026-December 2026

	2.4
	To actively participate in the development of CARICOM regional standards in at least nine (9) RTCs (or RTSCs) and host at least two (2) RTCs (or RTSCs) by December 31, 2026.


	2.4.1 Engage national stakeholders participating in regional standards development.

2.4.2 Circulate regional draft standards to the public for comments.

2.4.3 Conduct public consultations on draft regional standards

2.4.4 Collate national comments for submission to CROSQ Secretariat

2.4.5 Vote on Final Draft standards.

2.4.6 Adopt approved regional standards. 

2.4.7 Participates in TMC meetings.  

2.4.8 Prepare briefs for COTED on regional standards development.


	
	Number of CROSQ Regional Technical/Sub Committees participated in.

Number of TMC meetings participated in.


	Participation in Regional Technical Committees.

Adoption of CARICOM standards.


	
	Harmonisation of regional standards resulting in more local products and services accessing the regional markets.


	January 2026-December 2026

	2.5
	To collaborate with at least five (5) international bodies on standardisation matters during 2026.


	2.5.1 Participate in ISO activities. 

2.5.2 Participate in ASTM activities.

2.5.3 Participate in other standard developing organisations (SDOs) activities (API, UL, IEC, SAC)
	
	Number of ISO, IEC and ASTM activities participated in. 


	Active participation 


	
	Increased input in the development and acceptance of international standards by stakeholders.

	January 2026- December 2026 

	2.6
	To host the National Codex Secretariat for 2025 and facilitate at least four (4) National Codex Committee meetings.
	2.6.1 Host the Secretariat for the National Codex Contact Point (CCP)  

2.6.2 Participate in the National Codex Committee meetings.

2.6.3 Train regulators, food business operators and other food safety stakeholders on Codex standards.
	
	Secretariat hosted

No. of promotional activities completed.

Number of NCC meetings held. 

Number of stakeholders/participants trained. 

Percentage Completed Communications strategy

	Quarterly meetings

Minutes of meetings

Codex Standards promoted 

Promotional activities

Trained stakeholders 

Communication strategy 
	
	Protection of human, animal, and plant health and the environment. 


	January 2026-December 2026

	2.7
	To publish and have available for sale at least thirty (33) new, revised, confirmed, adopted or adopted with modification or adopted via endorsement standards approved by the National Standards Council during 2026.


	2.7.1 Printing and binding of standards

2.7.2 Publishing of standards

2.7.3 Sale of standards 

2.7.4 Responding to the needs of visitors, clients or wider stakeholders.

2.7.5 Maintain a web-based platform to offer standards for sale
	
	Number of standards printed and bound

Number of standards published

Number of standards sold

Number of walk-in visitors tended to


	Bound standards

Published standards

Standards sold


	
	Implementation of standards by stakeholders.  
	January 2026-December 2026

	2.8
	To maintain the publications and documents in the Standardisation Department throughout 2026
	2.8.1 Update Categories of Standards publication 

2.8.2 Issue Standards loans

2.8.3 Retrieve and file media information related to the GNBS (clips)

2.8.4 Maintain inventory of standards, publications, documents and items in the Standardisation department.
	
	Percentage of categories of standards updated

Number of loans issued

Number of media clipping retrieved and stored
	Updated categories of standards

Loans  
	
	Effective Services provided to stakeholders 


	January 2026-December 2026

	2.9
	To operate the National WTO/TBT Enquiry Point in 2026.
	2.9.1 Operate the national WTO/TBT Enquiry Point 


	
	Percentage of requests from WTO members addressed


	Record of requests and enquiries from stakeholders.
	
	Effective Services provided to stakeholders 


	January 2026- December 2026


STANDARDS DEVELOPMENT WORK PLAN JANUARY 2026 – JUNE 2026
	No.
	TITLE OF STANDARD
	SECTOR
	TYPE OF PROCESS
	ICS CODE
	STATUS

	1.
	GYS 9-10: 2014, Specification for Labelling of commodities Part 10: Labelling of equipment, items and parts containing refrigerants
	Refrigerants
	Revision
	13.300
	Enquiry Draft

	2.
	GYS 9-5:2003, Specification for Labelling of commodities-Part 5: Labelling of furniture 
	Wood Products
	Revision
	97.140
	Committee Draft

	3.
	GYS 19: 2003, Specification for Vinegar
	Food
	Revision
	67.220.20
	Final Draft

	4.
	GCP 20: 2004, Code of Practice for Street vended foods
	Food
	Revision
	67.230
	Final Draft

	5.
	GYS 193: 2017, Specification for Domestic gas stoves for use with liquefied petroleum gases
	Petroleum products
	Review
	97.040.20
	Preparatory

	6.
	GCP 6: 1997, Code of Practice for Persons carrying out the business of beautifying and improving the skin, hair and nails
	Cosmetics
	Revision
	71.100.70
	Preparatory

	7.
	BNS EAA 002:2017, Road Vehicles – Code of Practice for Inspection and Testing of Used Motor Vehicles for Roadworthiness
	Used motor vehicles
	Modified Adoption
	-
	Enquiry Draft

	8.
	General requirements for Installation and Inspection of Elevators/Lifts (ISO 8100-1: 2019- Lifts for the transport of persons and goods — Part 1: Safety rules for the construction and installation of passenger and goods passenger lifts)
	Elevators
	Modified Adoption
	-
	Enquiry Draft

	9.
	GYS 583: 2021 Requirements for Sale of used motor vehicles
	Used Motor Vehicles
	Review
	43.080.01
	Final Draft

	10.
	GB 18384: 2020 (English), Electric Vehicles safety requirements 
	Electric Vehicles
	Modified Adoption
	-
	Committee Draft

	11. 
	GYS 169: 1998 Specification for the Content of warranties for goods
	Goods
	Revision
	
	Committee Draft

	12.
	GYS 9-17: 2025, Part 17- Specification for Labelling of protective helmets for road users
	Protective helmets
	Revision
	13.340.20
	Published

	13.
	GYS 264: 2025, Specification for the Storage, handling and transportation of LPG cylinders
	LPG cylinders
	Revision
	75.160.30
	Published

	14.
	GYS 453: 2025, Specification for the Storage, handling and transport of steel compressed gas cylinders
	Gas cylinders
	Revision
	23.020.35
	Published

	15.
	GYS 523: 2018, Specification for low pressure regulators for use with Liquefied Petroleum Gas (LPG)
	Low pressure regulators
	Revision
	23.060.40; 75.160.20
	Published

	16.
	Standard for the design, construction, operation and maintenance of LPG transport tanks
	LPG tanks
	Development
	-
	Preparatory

	17.
	GYS 9-12: 2002, Specification for Labelling of commodities - Part 12: Labelling of toys and playthings
	Toys and playthings
	Review
	13.300
	Preparatory

	18.
	GYS 541: 2018 Specification for the Labelling, Packaging and Testing of Toys and Playthings


	Toys and playthings
	Review
	19.020 -13.300
	Preparatory

	19.
	GYS 67: 2017 (Amd. 2021) “Requirements for pneumatic passenger car tyres”
	Passenger car tyres
	Review
	83.160.10
	Preparatory

	20.
	Specification for Silver articles
	Silver articles
	Development
	-
	Enquiry Draft

	21.
	Specification for Platinum articles
	Platinum articles
	Development
	-
	Enquiry Draft

	22. 
	Specification for Palladium articles
	Palladium articles
	Development
	-
	Enquiry Draft

	23.
	ISO 24016: 2020, Jewellery and precious metals- Grading of polished diamonds- Terminology, classification and test methods
	Jewellery
	Adoption
	-
	Final Draft

	24.
	ISO 18323: 2015, Jewellery- Consumer confidence in the diamond industry
	Jewellery
	Adoption
	-
	Final Draft

	25.
	ISO 15093: 2020, Jewellery and precious metals- Determination of high purity gold, platinum and palladium- Difference method using ICP- OES
	Jewellery
	Adoption
	-
	Final Draft

	26.
	ISO 6893: 2024, Jewellery and precious metals- Inspection of batches of small diamonds- Terminology, classification and test methods
	Jewellery
	Adoption
	-
	Final Draft

	27.
	ISO 24018: 2020, Jewellery and precious metals- Specifications for 1 kilogram gold bar
	Jewellery
	Adoption
	-
	Final Draft

	28.
	GYS 170: 2021, General operations of a laboratory
	Laboratory
	Revision
	03.120.20; 19.020
	Preparatory


STANDARDS UNDERGOING REVIEW
	National Review

	GYS 193: 2017, Specification for Domestic gas stoves for use with liquefied petroleum gases

	GYS 264: 2021, Specification for the Storage, handling and transportation of LPG cylinders

	GYS 453: 2021, Specification for the Storage, handling and transport of steel compressed gas cylinders

	GYS 523: 2018, Specification for Low pressure regulators for use with Liquefied Petroleum Gas (LPG)

	

	GYS 169: 1998, Specification for the Content of warranties for goods

	GYS 28: 2006, Specification for Safety matches

	GYS 173: 1998, Glossary of terms relating to textile and clothing

	GYS 174: 1998, Methods of test for the determination of dimensional change in washing and drying of textiles

	

	GYS 16: 1995, Specification for Sugar for canning

	GYS 61: 1996, Specification for Grades of eddoe

	GYS 62: 1996, Specification for Grades of boulanger (Eggplant)

	GYS 9-17: 2019, Part 17- Specification for Labelling of protective helmets for road users

	

	GCP 9-5: 1999, Building Code – Section 5: Plumbing

	GYS 583: 2021, Requirements for Sale of used motor vehicles

	GYS 67: 2017 (Amd. 2021) Requirements for Pneumatic passenger car tyres

	GYS 213: 2002, Specification for Liquid household chlorine bleaches


END OF DOCUMENT
2 | Page

